|  |  |  | Company Project No. 0123456789 ESTIMATE EXECUTION PLAN |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | REVISIONS |  | APPROVALS |  |  |
| REV | DATE | PAGES | DESCRIPTION | BY | EST. MGR. | PRJ. MGR. |  |
| A |  |  | Issued for Approval |  |  |  |  |

# ESTIMATE PLAN

## INDEX

1.0 INTRODUCTION

1.1 Purpose of the Estimate Plan

2.0 ESTIMATE ORGANIZATION

2.1 Work Breakdown Structure

2.2 Code Of Accounts

2.3 Estimate Format

3.0 ESTIMATE METHODOLOGY

3.1 Direct Costs

3.2 Labor Cost Pricing Basis

3.3 Mechanical Equipment Pricing

3.4 Construction Indirect Costs

3.5 Engineering

3.6 Other Costs

4.0 BELOW LINE COSTS

5.0 ESCALATION & CONT

5.1 Escalation

5.2 Contingency

6.0 EXCLUSIONS and CLIENT COSTS

6.1 Exclusions

6.2 Client Costs

7.0 ATTACHMENTS

Attachment # 1 - Conceptual Phase Schedule and Deliverables

Attachment # 2 - Estimate Responsibility Matrix

Attachment # 3 - Work Breakdown Structure

Attachment # 4 - Total Estimate Format

Attachment # 5 - Specification Requirements

Attachment # 6 - Discipline Listing of Items Required to Complete Scope

Attachment # 7 - Minimum Requirements for Equipment Input

Attachment # 8 - Summary of Proposed ACCE Basis Settings and Default Selection

### ESTIMATE PLAN

1.0. INTRODUCTION

#### 1.1 Purpose of the Estimate Plan

The purpose of this estimate plan is to provide guideline for preparation of the ____ Project +XX% / -YY% cost estimate including scoping, scheduling of estimating steps and work breakdown structure in order to achieve uniformity, consistency and clear presentation of the cost estimate.

2.0 ESTIMATE ORGANIZATION

#### 2.1 Work Breakdown Structure

The estimate will be developed in accordance with the project Work Breakdown Structure. This structure will reflect the physical and/or contractual boundaries of the work and provide the framework to organize and summarize the estimate.  The Work Breakdown Structure is included as attachment #3.

#### 2.2 Code Of Accounts

The details of the estimate will be in accordance with the standard Code Of Accounts used at ABC Company.

00 - Excavation and Civil

10 - Concrete

20 - Structural Steel

30 - Buildings

40 - Machinery and Equipment

50 - Piping

60 - Electrical

70 - Instruments

80 - Paint and Insulation

#### 2.3 Estimate Format

The estimate will be further broken down into major cost elements such as direct field cost (materials and subcontracts), indirect field costs and other costs (Engineering, ocean freight, spare parts, import duties, client costs, escalation, contingency and the like).  After the estimate alignment meeting a sample estimate format document will be issued.

#### 2.4 Key Estimate Dates

| Estimate Plan | 00/00/0000 |
| --- | --- |
| Scope Documents from Engineering | 00/00/0000 |
| Material Take-offs | 00/00/0000 |
| Scope Freeze Date* | 00/00/0000 |
| Bulk/SC Pricing | 00/00/0000 |
| Equipment Pricing | 00/00/0000 |
| Input from Construction (Performance) | 00/00/0000 |
| Assemble Estimate | 00/00/0000 |
| Reviews – Internal | 00/00/0000 |
| Reviews – External | 00/00/0000 |

2.5 Definitions

To be included as appropriate…

3.0 ESTIMATE METHODOLOGY

#### 3.1 Direct Costs

The direct costs will be generated by the estimating system.  The bulk quantities will be generated based on the mechanical equipment and project specifications.  Additional bulk quantities will be generated based off the plot plan.

00 - Excavation and Civil - Plot plans will be used to develop quantities for roads, parking, fencing, site drainage requirements etc.

10 - Concrete – Equipment foundations will be generated by the estimating system and reviewed by engineering.  Plot plan layouts will be used to develop quantities for interconnecting pipe supports and sleepers and miscellaneous other site concrete such as dike walls, concrete paving outside battery limit areas etc.

20 - Structural Steel - Plot plan layout will be used to develop quantities for interconnecting pipe supports (piperacks, T supports etc.).  The estimating group based on dimensions provided by engineering will develop the material for equipment structures.  The material quantities will be verified by engineering.

30 - Buildings – The building costs will be generated based on a dollar per ft2 basis and the type of building.

50 - Piping – Piping quantities will be generated by the estimating system based on the mechanical equipment and plot plan information.  The quantities will be supplemented for interconnecting piping.

60 - Electrical – The electrical scope will be generated by the estimating system based on mechanical equipment and geographical arrangement.  The cable runs will be determined by the distance to the MCC.  The lighting and grounding requirements will be determined from the plot plan and layout of equipment.

70 - Instrumentation --The field instrumentation will be generated by the estimating system based on the mechanical equipment.  The control systems will be determined by the I/O count generated by the estimating system.  The costs and scope of the control systems will be verified by engineering.

80 - Paint and Insulation - Paint and insulation for interconnecting pipe will be estimated based off the temperatures of the equipment.  If the carbon steel pipe is not insulated, it will be primed and painted.  If it is insulated, it will be primed only.  Stainless steel pipe will not be primed or painted.

#### 3.2 Labor Cost Pricing Basis

Labor costs will be estimated utilizing an open shop labor rate. The rate will include direct labor only.

#### 3.3 Mechanical Equipment Pricing

The estimating system will generate the mechanical equipment based on the equipment list provided by project.  This list will include sizes, pressures, temperatures, metallurgy, etc.  The minimum requirements for the mechanical equipment definition is included in attachment 7.  The pricing will be reviewed and where applicable replaced by in-house pricing.

#### 3.4 Construction Indirect Costs

The scope covered by construction indirect costs include:

- Temporary Construction Facility

- Construction Services, Supplies and Expense

- Construction Equipment

- Field Staff

- Payroll Benefits and Burdens

- Engineering Support During Construction

Construction indirect costs will be estimated as a percentage of direct field costs based on in-house historical information.

#### 3.5 Engineering

Engineering costs will be estimated as a percentage of total field costs. This percentage will be based on in-house historical information and will include engineering, procurement and other support services required by the contractor.

#### 3.6 Other Costs

The following items will be included as part of the lump sum contractor other costs:

Inland Freight - Inland freight costs will be estimated as a percent of material costs based on in-house historical information.

Ocean Freight – Ocean freight will be excluded from the estimate.

Vendor Reps - Costs will be estimated based on a listing of the items requiring field vendor assistance.

Sales Taxes - Costs for sales taxes will be estimated and included at 8% per Customer.

Contractor Fee - Fee will be included as a percent of total cost.

Team Building – An allowance will be made.

Incentive Costs – Will be included for home office and field labor hours and construction management.

#### 4.0 BELOW LINE COSTS

The following items will be included as part of the below line costs:

Catalyst and Chemicals – E&C to provide a list of the required catalyst and chemicals. Pricing of required catalyst and chemicals will be by Customer.

Capital Equipment Spares – Capital equipment spares are not included in the estimate.

5.0 ESCALATION and CONTINGENCY

#### 5.1 Escalation

The estimate will be prepared on a first quarter 20XX basis. Escalation will not be included in the details of the estimate, but estimated separately, and included in the estimate as a separate line item.

#### 5.2 Contingency

The recommended contingency will be based on a detailed risk analysis utilizing an in-house Monte Carlo range estimating program.

6.0 EXCLUSIONS and CLIENT COSTS

#### 6.1 Exclusions

Listed below are items excluded from COMPANY scope of the estimate:

- Pre-investment or allowance for future capacity expansion

- VAT, duties and / or import taxes that may be applicable

- Builders all risk insurance, bid bonds, bank guarantees,

- Force majeure (to include war, civil unrest, acts of government, named storms, earthquakes and other natural disasters cultural restrictions and industrial disturbance)

- Undefined scope

- Overall schedule impacts

- Land costs – if any

- Project development costs

#### 6.2 Client Costs

Following is a list items that will be included as part of the client costs.

E&C can assist Customer in scoping and estimating these costs if required:

- Program management

- Pre-commissioning and start up

- Cost of utilities required during start up

- Capital equipment spares

- Warehouse spares

- Catalyst and chemicals

- Consultants (soil, IPA, teambuilding, HAZOP, etc.)

- Insurance (builders risk, start up delay / loss of profit, general liability, marine cargo etc.)

- License fees, royalties

- Permits (environmental, building etc.)

- Environmental assessment

- Building furnishings / lab equipment

- Working capital

- Bank fees / interest

- Land costs

- Shared costs (possible pro rate share of existing infrastructure costs i.e. admin. building, control room, power plant, other utilities, railroad/ship loading facilities etc.)

- Power connection fees

- Currency fluctuations

- Import taxes and duties for owner costs

- Existing facilities shut down for tie-ins (loss of product)

#### 7.0 ATTACHMENTS

Attachment # 1 - Conceptual Phase Schedule and Deliverables

Attachment # 2 - Estimate Responsibility Matrix

Attachment # 3 - Work Breakdown Structure

Attachment # 4 - Total Estimate Format

Attachment # 5 - Specification Requirements

Attachment # 6 - Discipline Listing of Items Required to Complete Scope

Attachment # 7 - Minimum Requirements for Equipment Input

Attachment # 8 - Summary of Proposed ACCE Basis Settings and Default Selection